## VSS
Disease Prediction of Crops using IoT | Proposed Milestone Date | Proposed Milestone Date | References
VSS#0 | 02-Nov-2018 (End of Sprint 1) | Ideas for project | www.google.com
VSS#1 | 15-Nov-2018 (End of Sprint 2) | Problem selection
VSS#2 | 27-Nov-2018 (End of Sprint 3) | Technology selection | https://www.IOTforall.com/IOT-applications-in-agriculture/
VSS#3 | 06-Dec-2018 (End of Sprint 4) | Budget disscusion of project.
VSS#4 | 19-Dec-2018 (End of Sprint 5) | Visit to the Crystal inspired growth plant pharmacy ,Karad to get their datasets for chilly, watermelon, wheat, gram, corn, etc. | https://data.gov.in/catalogs/sector/agriculture-9212
VSS#5 | 02-Jan-2019 (End of Sprint 6) | Installation of all requisites on the machine. | https://www.realvnc.com/en/connect/download/viewer/windows/
VSS#6 | 11-Jan-2019 (End of Sprint 7) | Buying sensors , Raspberry pi kit and setup for implementation. | https://www.youtube.com/watch?v=Zhd-i6DKlAU
VSS#7 | 23-Jan-2019 (End of Sprint 8) | Design part for Disease prediction system is done. | https://www.jetbrains.com/pycharm/
VSS#8 | 01-Feb-2019 (End of Sprint 9) | Coding in python based on datasets we have got through Crystal inspired growth and also for sending alert or notification by using What's app message. | https://www.w3schools.com/python/python_mysql_select.asp
VSS#9 | 04-March-2019 (End of Sprint 10) | Testing of system on specific crops.
VSS#10 | 19-March-2019(End of Sprint 11) | Improvement in coding for more accuracy and code coplexity deduction, Preparing for research paper (to present in journal and conference). | https://www.twilio.com/
VSS#11 | 02-April-2019(End of Sprint 12) | Implementation of system on specific crop after good results in testing. Research paper completed.
VSS#12 | 08-April-2019(End of Sprint 13) | Project completed and Research paper get approved by IJERT and Writing report in latex format.
VSS#13 | 20-April-2019(End of Sprint 14) | Presented our project in QUANTUM.

## Comm
A git repo will be provided by Mini project Incharge where all the code should be checked in.
Bi-weekly meeting will be held for regular sync up and feedback. Days can be flexible, proposed is Monday and Friday
Choice of library / frameworks are flexible
Guide will provide necessary help during the completion of project
All the relevant formats & sheets are made available on MOODLE server.
Make the best use of Mini project Practical hours.
Continuously engage with guide.